## Slide 1
BSW Academy Foundation Quality Improvement
Sarah White
Improvement Lead
August 2023

## Slide 2
What is covered in this session
What is Quality Improvement?
Some Tools and Techniques
How to use A3 Thinking method
Notes: This session will look at what we mean by Quality Improvement, some of the common tools and techniques and also how to use A3 Thinking to help plan and deliver your QI project

## Slide 3
Some QI Approaches
IHI Model for Improvement
Project Management
Lean
Improving Together
Quality, Service Improvement and Redesign (QSIR)
Notes: There are a lot of approaches available in BSW and you may have heard of some of these

## Slide 4
Some QI Approaches
IHI Model for Improvement
Project Management
Lean
Improving Together
Quality, Service Improvement and Redesign (QSIR)
Notes: IHI model for improvement is most common
Lean is good for identifying waste in process
We have QSIR which uses many of the tools we will talk about in the course
Improving Together has been adopted by the 3 Acutes in BSW
Project management is also key

## Slide 5
Key stages of all Improvement activity
Understand the problem
Design Improvement
Data and Measurement
Implement Change
Test Ideas
Notes: All improvement follows the same basic steps

## Slide 6
Health Foundation Definition of QI
Quality improvement involves the use of a systematic and coordinated approach to solving a problem using specific methods and tools with the aim of bringing about a measurable improvement within a health care setting.
Notes: Definition of Quality Improvement

## Slide 7
Put more simply…
Quality improvement is a systematic approach to solving a problem using a range of tools to make measurable improvement for patients
Notes: Simplified – emphasis on systematic and measureable

## Slide 8
Quality Improvement Tools for your Toolbox
A3 Thinking
SMART Aims
Process Flows
Fishbone Analysis
5 Whys
PDSA Cycles
Notes: Quality Improvers use tools

## Slide 9
A3 Thinking
SMART Aims
Process Flows
Fishbone Analysis
5 Whys
PDSA Cycles
Quality Improvement Tools for your Toolbox
Notes: Some of the tools that participants may have heard of or used and useful to have in the toolbox
10

## Slide 10
Why Use A3 Thinking?
BSW approach
Tool to help you describe and design your improvement
Dynamic document
Helps to engage with stakeholders
Notes: Underpinning improvement activity is the roadmap – A3 thinking helps to outline the stages referred to earlier and hone a groups thinking
11

## Slide 11
Step 1: Problem Statement
What problem are you trying to solve?
How do we quantify the problem?
Step 2: Current Situation
  What is the current process
  What is the team doing?
  What are we measuring?
Step 7. Reflect and Learn
  Did you achieve your goal?
  How many PDSA cycles did you do?
  What did we learn?
Step 5: Design the Improvement
  What are you proposing to change?
  How are you planning to change it?
  Why was this change chosen?
Step 4: Root Cause Analysis
  What is the root cause of the issue?
Step 6: Tests of Change
  What is the timeline How long will this take?
  Who will be on the project team?
  Who is responsible for what?
Step 3: Vision/Goals
  What is the overall vision?
  What is the goal?
  How will you know it is successful?
A3 THINKING WORKSHEET

## Slide 12
Step 1: Problem Statement
What problem are you trying to solve?
How do we quantify the problem?
Step 2: Current Situation
  What is the current process
  What is the team doing?
  What are we measuring?
Step 7. Reflect and Learn
  Did you achieve your goal?
  How many PDSA cycles did you do?
  What did we learn?
Step 5: Design the Improvement
  What are you proposing to change?
  How are you planning to change it?
  Why was this change chosen?
Step 4: Root Cause Analysis
  What is the root cause of the issue?
Step 6: Tests of Change
  What is the timeline How long will this take?
  Who will be on the project team?
  Who is responsible for what?
Step 3: Vision/Goals
  What is the overall vision?
  What is the goal?
  How will you know it is successful?
A3 THINKING WORKSHEET
PLAN
PLAN
PLAN
PLAN
PLAN
DO/STUDY
ACT

## Slide 13
Start by understanding the problem
This can be harder than it seems
Group work helps to build consensus
Planning is the crucial
Involve everyone
Define the aim of the project
Notes: Thinking about the first part of A3, the first task is define the problem, where has the impetus for change come from, this is important in planning your intervention. The key is to be able to translate the overarching aim to something that is doable
15

## Slide 14
Our leaflets are out of date!!
Some patients have received incorrect information
We could…
Reprint the incorrect leaflets when they come to our attention
Pass the problem to someone else to deal with
See if we can solve the problem ourselves – with a QI Project
Let’s work through an example of a QI Project

## Slide 15
Who needs to be involved?
The first thing is identifying the stakeholders
Patients
Admin Team
Clinical Experts
Finance Team
Printers
Communications Leads
Who are the people you will need to work with to make this improvement?
Notes: Group discussion
17

## Slide 16
Who needs to be involved?
The stakeholders are the key to creating an improvement and making your change sustainable
Patients
Admin Team
Clinical Experts
Finance Team
External Agencies
Communications Leads
Notes: Group discussion
17

## Slide 17
Step 1: Problem Statement
What problem are you trying to solve?
How do we quantify the problem?
Step 2: Current Situation
  What is the current process
  What is the team doing?
  What are we measuring?
A3 THINKING WORKSHEET
You could hold a workshop to explore these ideas.
Ask you stakeholders to answer the questions from their point of view

## Slide 18
Step 1: Problem Statement
Step 2: Current Situation
A3 THINKING WORKSHEET
You might find that:
It's hard to define the problem without discussion
Is it all the leaflets?
What format are the leaflets in?
How big is the problem?
Who updates them now?
How often are leaflets reviewed?
Is there an actual process for leaflet reviews
Who needs to approve or sign off updates?

## Slide 19
Step 3: Vision/Goals
  What is the overall vision?
Notes: 22

## Slide 20
This project aims to ensure that all the leaflets are clinically correct and safe for patient use
The project will review all the leaflets held by the practise, update them, check to see if they’re already on the website and if not, upload them. The project will also make sure that all the leaflets are regularly reviewed
This project aims to review the process for updating leaflets held by the practise, the project will update the all information and circulate by September 2023

## Slide 21
The project will create a new, defined and articulated process for updating leaflets within the practise. The new process will be launched within Practise A in October 2023 and reviewed December 2023
Specific - create a new, defined and articulated process
Measurable – Has a process been created?
Achievable – This can be done effectively
Realistic – Yes, it’s creating a new process
Timebound – October 2023

## Slide 22
Step 4: Root Cause Analysis
Techniques to dig deeper:
Looking closely at the issue

## Slide 23
Fishbone Analysis
    Cause and effect to look at underlying factors
Cause and effect
    Gain insight from the team
Gain
    Use to determine why a particular problem is occurring
Use
Notes: Has anyone used a fishbone? Developed in Japanese industry, it’s a literal fish with bones and spines that help to categorise some of the challenges and help groups to think where the biggest issue sits
28

## Slide 24
Leaflets are out of date
Place
Providers
Process
People
On website and hard copies
Person who did leaflets has left
No time to do this
I don’t know how to update leaflets
We rely on other agencies for the information
Admin team do this?
Printers take ages
Who signs them off?
Need clinical input
Distribute to other sites
Patients getting info that’s wrong

## Slide 25
5 Whys
Why are they out date?
The leaflets are out of date
Why doesn’t anyone update them
Why hasn’t that task been allocated to new person?
Why doesn’t anyone know what the process is?
Why wasn’t it written down
Nobody updates them
Person who did it has left
Nobody knows what the process is
It was never written down
It was a task undertaken by one person with the implicit knowledge
Notes: Simple approach to start the conversation and to drill into the root cause.
30

## Slide 26
Use process mapping to get a better understanding of how a whole pathway works. If changes are made without understanding the current processes issues may occur at another point in the journey.
TASK
DECISION
TASK
TASK
TASK
DECISION
Notes: What is the learning? Would another technique have worked better?
Did you get to a root cause?
33

## Slide 27
Leaflets Process

## Slide 28
Step 5: Design the Improvement
Plan
Do
Study
Act
Well known improvement tool
This fits nicely into the A3 Thinking model

## Slide 29
Plan
Do
Study
Act
What happened when you carried out your test?
What did the data show?
Did the change result in an improvement?
What have you noticed?
Were there any unexpected outcomes?
Will you ADOPT the change, ADAPT it or ABANDON it?
Will you do another PDSA cycle
What will you change or test?
Have you got a baseline data set?
What do you predict will happen?

## Slide 30
Remember!
This is Rapid Cycle Improvement
Fail stands for First Attempt in Learning!
Doing is only 25% of the circle
It’s an iterative process

## Slide 31
Step 6: Tests of Change
P
S
A
D
P
S
A
D
P
S
A
D
P
S
A
D
DATA
Sustained improvement
Change Ideas

## Slide 32
Step 7. Reflect and Learn
Evaluation
Analysis
Improve
Feedback
Check

## Slide 33
Step 7. Reflect and Learn
Evaluation
Analysis
Improve
Feedback
Check

## Slide 34
Further Information and downloadable resources can be found at:
https://bswtogether.org.uk/academy/home/improvement/
Or by emailing sarah.white120@nhs.net
Notes: Quick round of introductions –
4